## Sheet1
Task Mode | WBS | Task Name | Duration | Start | Finish | Predecessors | Critical | Start Slack | Resource Names | Cost | Activities whose cost is lost
Auto Scheduled | 1.3.1.1.1 | Network module | 21 days | Mon 3/6/23 | Mon 4/3/23 | 12 | No | 49 days |  | 0
Auto Scheduled | 1.3.1.1.2 | Processor design | 21 days | Mon 3/6/23 | Mon 4/3/23 | 12 | No | 49 days |  | 0
Auto Scheduled | 1.3.1.1.3 | GPU and RAM | 7 days | Mon 3/6/23 | Tue 3/14/23 | 12 | No | 63 days |  | 0
Auto Scheduled | 1.3.1.1.4 | Storage and optical drive | 21 days | Mon 3/6/23 | Mon 4/3/23 | 12 | No | 49 days |  | 0
Auto Scheduled | 1.3.1.1.5 | Sensors | 21 days | Mon 3/6/23 | Mon 4/3/23 | 12 | No | 49 days |  | 0
Auto Scheduled | 1.3.1.2 | Panel design | 21 days | Mon 3/6/23 | Mon 4/3/23 |  | No | 49 days |  | 0
Auto Scheduled | 1.3.1.2.1 | Metal casing | 21 days | Mon 3/6/23 | Mon 4/3/23 | 12 | No | 49 days |  | 0
Auto Scheduled | 1.3.1.2.2 | Display | 7 days | Mon 3/6/23 | Tue 3/14/23 | 12 | No | 63 days |  | 0
Auto Scheduled | 1.3.1.2.3 | Switches | 7 days | Mon 3/6/23 | Tue 3/14/23 | 12 | No | 63 days |  | 0
Auto Scheduled | 1.3.1.3 | Hardware doccumentation | 5 days | Tue 4/4/23 | Mon 4/10/23 | 16,17,18,19,20,22,23,24 | No | 49 days |  | 0
Auto Scheduled | 1.3.2 | Software development | 75 days | Mon 3/6/23 | Fri 6/16/23 |  | Yes | 0 days |  | 0
Auto Scheduled | 1.3.2.1 | UI design | 60 days | Mon 3/6/23 | Fri 5/26/23 | 12 | No | 10 days |  | 0
Auto Scheduled | 1.3.2.2 | Patch design | 70 days | Mon 3/6/23 | Fri 6/9/23 | 12 | Yes | 0 days |  | 0