## Sheet1
Task Name | Duration | Possible Crash time | Cost per day | Additonal team |  | Possible Crashing Cost | Baseline Duration | Critical | Cost | Baseline Cost
Define project scope and objectives | 5 days | NA |  |  |  |  | 5 days | Yes | 4000 | 4000
Develop project schedule | 7 days | NA |  |  |  |  | 7 days | Yes | 10360 | 10360
Establish project budget | 7 days | NA |  |  |  |  | 7 days | Yes | 11200 | 11200
Assemble project team | 2 days | NA |  |  |  |  | 2 days | No | 1600 | 1600
Develop project communication plan | 2 days | NA |  |  |  |  | 2 days | No | 1600 | 1600
Conduct market research | 12 days | NA |  |  |  |  | 12 days | Yes | 7200 | 7200
Define product requirements | 7 days | NA |  |  |  |  | 7 days | Yes | 9800 | 9800
Develop product concept | 7 days | NA |  |  |  |  | 7 days | Yes | 5600 | 5600
Evaluate and select initial product design | 7 days | NA |  |  |  |  | 7 days | Yes | 10360 | 10360
Business Process Outsourcing | 14 days | NA |  |  |  |  | 14 days | Yes | 30800 | 30800
Network module | 21 days | [5 empty] | 21 days | No | 31080 | 31080
Processor design | 21 days | [5 empty] | 21 days | No | 31080 | 31080
GPU and RAM | 7 days | [5 empty] | 7 days | No | 10360 | 10360
Storage and optical drive | 21 days | [5 empty] | 21 days | No | 31080 | 31080
Sensors | 21 days | [5 empty] | 21 days | No | 31080 | 31080
Metal casing | 21 days | [5 empty] | 21 days | No | 31080 | 31080
Display | 7 days | [5 empty] | 7 days | No | 10360 | 10360
Switches | 7 days | [5 empty] | 7 days | No | 10360 | 10360
Hardware doccumentation | 5 days | [5 empty] | 5 days | No | 3000 | 3000
UI design | 45 days | 10 | 680 | 1 | DEV | 6800 | 45 days | Yes | 73400 | 66600
Patch design | 67 days | 12 | 680 | 2 | DEV | 16320 | 67 days | Yes | 115480 | 99160
Software documentation | 3 days | 1 | 600 | 1 | DOC | 600 | 3 days | Yes | 5040 | 4440
Design verification and validation | 5 days | 0 |  |  |  |  | 5 days | Yes | 7400 | 7400
Source components and material | 18 days | 8 | 600 | 2 | Procurement | 9600 | 18 days | Yes | 20400 | 10800
Finalize component contracts | 7 days | 0 |  |  |  |  | 7 days | Yes | 4200 | 4200
Manage component delivery schedule | 7 days | 0 |  |  |  |  | 7 days | Yes | 4200 | 4200
Prototype design | 12 days | 0 |  |  |  |  | 12 days | Yes | 15840 | 15840
Prototype assembly | 5 days | 0 |  |  |  |  | 5 days | Yes | 6600 | 6600
Prototype testing | 7 days | 0 |  |  |  |  | 7 days | Yes | 19320 | 19320
Addressing any design issues or defects | 7 days | [5 empty] | 7 days | Yes | 14840 | 14840
Establish production process | 50 days | [5 empty] | 50 days | No | 32000 | 32000
Assembly and batch maufacturing | 7 days | 0 |  |  |  |  | 7 days | Yes | 4480 | 4480
Qualiity control and Rolling out first batch | 3 days | 1 | 600 | 1 | A&T | 600 | 3 days | Yes | 4440 | 3840
33920
[9 empty] | 609640 | 575720
33920