## Old
Task Name | Duration | Critical | Optimistic Duration | Most Likely Duration | Pessimistic Duration | Expected Duration | Standard Deviation
Define project scope and objectives | 5 | Yes | 4 | 5 | 6 | 5 | 1.67
Develop project schedule | 7 | Yes | 6 | 7 | 8 | 7 | 2.33
Establish project budget | 7 | Yes | 6 | 7 | 8 | 7 | 2.33
Assemble project team | 2 | No | 1 | 2 | 3 | 2 | 0.67
Develop project communication plan | 2 | No | 1 | 2 | 3 | 2 | 0.67
Conduct market research | 12 | Yes | 10 | 12 | 14 | 12 | 4
Define product requirements | 7 | Yes | 6 | 7 | 8 | 7 | 2.33
Develop product concept | 7 | Yes | 6 | 7 | 8 | 7 | 2.33
Evaluate and select initial product design | 7 | Yes | 6 | 7 | 8 | 7 | 2.33
Business Process Outsourcing | 14 | Yes | 12 | 14 | 16 | 14 | 4.67
Network module | 21 | No | 18 | 21 | 24 | 21 | 7
Processor design | 21 | No | 18 | 21 | 24 | 21 | 7
GPU and RAM | 7 | No | 6 | 7 | 8 | 7 | 2.33
Storage and optical drive | 21 | No | 18 | 21 | 24 | 21 | 7
Sensors | 21 | No | 18 | 21 | 24 | 21 | 7
Metal casing | 21 | No | 18 | 21 | 24 | 21 | 7
Display | 7 | No | 6 | 7 | 8 | 7 | 2.33
Switches | 7 | No | 6 | 7 | 8 | 7 | 2.33
Hardware doccumentation | 5 | No | 4 | 5 | 6 | 5 | 1.67
UI design | 35 | Yes | 30 | 35 | 40 | 40 | 13.33
Patch design | 55 | Yes | 48 | 55 | 60 | 61.67 | 21.67
Software documentation | 3 | Yes | 2 | 2 | 4 | 2.33 | 1
Design verification and validation | 5 | Yes | 4 | 5 | 6 | 5 | 1.67
Source components and material | 18 | Yes | 8 | 10 | 15 | 11.67 | 5
Finalize component contracts | 7 | Yes | 6 | 7 | 8 | 7 | 2.33
Manage component delivery schedule | 7 | Yes | 5 | 7 | 8 | 7 | 2.33
Prototype design | 12 | Yes | 10 | 12 | 14 | 12 | 4
Prototype assembly | 5 | Yes | 3 | 5 | 6 | 5 | 1.67
Prototype testing | 7 | Yes | 4 | 5 | 7 | 7 | 2.33
Addressing any design issues or defects | 7 | Yes | 5 | 7 | 8 | 7 | 2.33
Establish production process | 50 | No | 45 | 50 | 52 | 50.83 | 17.5
Assembly and batch maufacturing | 7 | Yes | 6 | 7 | 8 | 7 | 2.33
Qualiity control and Rolling out first batch | 3 | Yes | 2 | 2 | 4 | 2.33 | 1
Optimistic Duration | 212 |  | 2023-10-24
Most Likely Duration | 235 |  | 2023-11-24
Pessimistic Duration | 282 |  | 2024-01-30
[5 empty] | Mean | Mode | Max
#NAME?

## Final
Critical Tasks | Optimistic Duration | Most Likely Duration | Pessimistic Duration | PERT Expected Time | Standard Deviation | Variance
Define project scope and objectives | 4 | 5 | 6 | 5 | 0.33 | 0.1089
Develop project schedule | 6 | 7 | 8 | 7 | 0.33 | 0.1089
Establish project budget | 6 | 7 | 8 | 7 | 0.33 | 0.1089
Conduct market research | 10 | 12 | 14 | 12 | 0.667 | 0.44489
Define product requirements | 6 | 7 | 8 | 7 | 0.33 | 0.1089
Develop product concept | 6 | 7 | 8 | 7 | 0.33 | 0.1089
Evaluate and select initial product design | 6 | 7 | 8 | 7 | 0.33 | 0.1089
Business Process Outsourcing | 12 | 14 | 16 | 14 | 0.667 | 0.44489
UI Design | 30 | 35 | 40 | 35 | 1.667 | 2.7789
Patch Design | 45 | 53 | 58 | 52.5 | 2.167 | 4.6959
Software documentation | 2 | 2 | 3 | 2.167 | 0.167 | 0.027889
Design verification and validation | 4 | 5 | 6 | 5 | 0.33 | 0.1089
Source components and material | 8 | 10 | 15 | 10.5 | 1.167 | 1.3619
Finalize component contracts | 6 | 7 | 8 | 7 | 0.33 | 0.1089
Manage component delivery schedule | 5 | 7 | 8 | 6.833 | 0.5 | 0.25
Prototype design | 10 | 12 | 14 | 12 | 0.667 | 0.44489
Prototype assembly | 3 | 5 | 6 | 4.833 | 0.5 | 0.25
Prototype testing | 4 | 5 | 7 | 5.167 | 0.5 | 0.25
Addressing any design issues or defects | 5 | 7 | 8 | 6.833 | 0.5 | 0.25
Assembly and batch maufacturing | 6 | 7 | 8 | 7 | 0.33 | 0.1089
Qualiity control and Rolling out first batch | 2 | 3 | 4 | 3 | 0.33 | 0.1089
Summation |  |  |  | 223.833 |  | 12.2882
Probability of Success of the Project
Z | 1.7593
Probability of Completion (%) | 96.062